## Backlog
Current Sprint: 1
ID | Task | Estimated Hours | Priority | Sprint When Finished | Responsible Parties
1 | Look through previous GitHub repository | 8 | 4 | 1 | Khushi
2 | Look at UA Blount website pages for desireable features | 2 | 4 | 1 | All
3 | Draft mobile homescreen design | 2 | 1 | 1 | Nicholas
4 | Draft desktop homescreen design | 2 | 1 | 1 | Nicholas
5 | Cybersecurity research | 8 | 1 | 1 | Andres
6 | Create new blount compass homepage | 2 | 1 | 1 | Nicholas
7 | Edit site theming for header and footer | 4 | 2 | 1 | Nicholas
8 | Draft room schedule tracker page design | 1 | 5 | 1 | Hannah
9 | Facilitate access to WordPress | 1 | 1 | 1 | Chandler
10 | Create room schedule tracker events | 1 | 2 | 1 | Hannah
11 | Find booking plug-in to adapt for room tracker | 2 | 1 | 1 | Hannah
12 | Find job board plug-in to adapt for rideshare | 2 | 1 | 1 | Khushi / Andres
13 | Upload and activate job board plugin to wordpress | 1 | 1 | 1 | Khushi
14 | Draft rideshare UI | 4 | 3 | 1 | Khushi / Andres
15 | Re-route links to the static Blount website to open new tabs / windows *OR* implement Whiting's quick-link list | 3 | 3
16 | Decide on overall navigation flow from home page | 3 | 3
17 | Color timeline differently based on which room was selected | 12 | 2 |  | Hannah
18 | Divide timeline based on number of rooms available | 10 | 3 |  | Hannah
19 | Allow for date select from timeline on room tracker | 10 | 5 |  | Hannah
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!