## Backlog
Current Sprint: 2
ID | Task | Estimated Hours | Priority | Sprint When Finished | Responsible Parties
1 | Look through previous GitHub repository | 8 | 4 | 1 | Khushi
2 | Look at UA Blount website pages for desireable features | 2 | 4 | 1 | All
3 | Draft mobile homescreen design | 2 | 1 | 1 | Nicholas
4 | Draft desktop homescreen design | 2 | 1 | 1 | Nicholas
5 | Cybersecurity research | 8 | 1 | 1 | Andres
6 | Create new blount compass homepage | 2 | 1 | 1 | Nicholas
7 | Edit site theming for header and footer | 4 | 2 | 1 | Nicholas
8 | Draft room schedule tracker page design | 1 | 5 | 1 | Hannah
9 | Facilitate access to WordPress | 1 | 1 | 1 | Chandler
10 | Create room schedule tracker events | 1 | 2 | 1 | Hannah
11 | Find booking plug-in to adapt for room tracker | 2 | 1 | 1 | Hannah
12 | Find job board plug-in to adapt for rideshare | 2 | 1 | 1 | Khushi / Andres
13 | Upload and activate job board plugin to wordpress | 1 | 1 | 1 | Khushi
14 | Draft rideshare UI | 4 | 3 | 1 | Khushi / Andres
15 | Re-route links to the static Blount website to open new tabs / windows *OR* implement Whiting's quick-link list | 3 | 3 | 1 | Chandler
16 | Create and integrate about page | 10 | 2 | 1 | Chandler
17 | Decide on overall navigation flow from home page | 3 | 3 | 2 | Chandler
18 | Divide timeline based on number of rooms available | 10 | 3 | 2 | Hannah
19 | Create section landing pages | 2 | 3 | 2 | Nicholas
20 | Update nav menu to contain only section that are section on home page | 2 | 3 | 2 | Nicholas
21 | Create the around town page | 2 | 3 | 2 | Nicholas
22 | Research what to include for the around town page | 1 | 4 | 2 | Nicholas
23 | Retrieve parsed appointment info from the SQL server | 5 | 1 | 2 | Hannah
24 | Display room bookings by room instead of by day | 10 | 1 | 2 | Hannah
25 | Add OAuth plugin to allow UA system microsoft OAuth | 3 | 1 | 2 | Nicholas
26 | Restrict some pages to allow only logged in user access | 1 | 2 | 2 | Nicholas
27 | Research how to modifyy the fixed/inaccesible plugin files | 5 | 1 | 2 | Khushi
27 | Analyze and understand job board plugin codebase | 4 | 2 | 2 | Andres
28 | Modify PHP files in job board plugin for ride share usage | 10 | 1 | 2 | Khushi / Andres
29 | Override the fixed "job" lingo via cPanel's file manager system | 4 | 1 | 2 | Khushi
30 | Place wp-job-manager/rideshare plugin files into GitHub for source control | 1 | 1 | 2 | Andres
31 | Create a ride share landing page (describe feature, links, etc) | 2 | 1 | 2 | Khushi
31 | Apply patches to plugin + create ride categories in WP Editor | 1 | 1 | 2 | Andres
32 | Fix navigation to the different ride share pages | 3 | 1 | 2 | Khushi
33 | Customize timeline appearance | 8 | 3 | 2 | Hannah
34 | Allow for date select from timeline on room tracker | 10 | 5 |  | Hannah
35 | Research plugins for News Feed and post submission | 4 | 3 | 2 | Chandler
36 | Design Navigation and layout for local, national, and overall news | 10 | 2 | 2 | Chandler
37 | Design and Implement User Submission for News posts | 8 | 2 | 2 | Chandler
38
39
40
41
42
43
44
45
46
47
48